## Sheet1
Main Tabs | Sub Tabs | Section | Feature | Phase | App Status | Test Status
Advisor |  | Landing | Intro page with example prompts; 'Coming soon' or waitlist | Phase 1 | Not Started | Pending
Advisor |  | Governance | Disclaimer (non‑advisory), privacy/PDPL note, citation policy | Phase 1 | Not Started | Pending
Advisor |  | Routing | Ask‑from‑dataset deep links route here with context stored | Phase 1 | Not Started | Pending
Advisor |  | Chat | Chat input; multiline; enter‑to‑send | Phase 2 | Not Started | Pending
Advisor |  | Citations | Answers include dataset citations with timestamps | Phase 2 | Not Started | Pending
Advisor |  | Charts | Inline simple charts (time‑series/bar) with PNG/CSV download | Phase 2 | Not Started | Pending
Advisor |  | Feedback | Thumbs up/down; copy answer; share link | Phase 2 | Not Started | Pending
Advisor |  | Context | Automatic context injection from current page (dataset/map/trade) | Phase 3 | Not Started | Pending
Advisor |  | Inspector | 'Show sources' and step summary to reduce hallucinations | Phase 3 | Not Started | Pending
Advisor |  | Export | Export conversation as PDF/CSV | Phase 3 | Not Started | Pending
Advisor |  | SQL/Code | Generate SQL for queryable datasets; export snippet | Phase 4 | Not Started | Pending
Advisor |  | Agentic Tasks | Multi‑step tasks (e.g., build a compare table then email) with review gates | Phase 5 | Not Started | Pending
Advisor |  | Plugins | Hook into Business Builder/Price Comparison to prefill inputs | Phase 5 | Not Started | Pending
Advisor | Agentic Tasks | Platform | Scheduled questions (weekly brief) with email delivery | Phase 5 | Not Started | Pending
Advisor | Prompts | Library | Curated prompt templates per role (policy, VC, SME) | Phase 2 | Not Started | Pending
Advisor | Prompts | Pinned | Pin favorite prompts | Phase 3 | Not Started | Pending
Advisor | Retrieval | Source Filters | Toggle which datasets/sources are allowed | Phase 3 | Not Started | Pending
Advisor | Retrieval | Time Filter | Limit answers to specific periods | Phase 3 | Not Started | Pending
Advisor | Reasoning | Show Work | 'Explain calculation' step-by-step | Phase 3 | Not Started | Pending
Advisor | Reasoning | Unit Safety | Unit detection and standardized conversions | Phase 3 | Not Started | Pending
Advisor | Privacy | Redaction | Redact PII from answers/logs | Phase 2 | Not Started | Pending
Advisor | Citations | Deep Links | Citation click jumps to dataset row/section | Phase 3 | Not Started | Pending
Advisor | Shortcuts | From Map/Trade | Right-click → 'Ask AI about selection' | Phase 3 | Not Started | Pending
Advisor | Exports | Email Brief | Send summarized brief to email | Phase 4 | Not Started | Pending
Advisor | Exports | Markdown/CSV | Export answers as Markdown/CSV | Phase 2 | Not Started | Pending
Advisor | Controls | Temperature | Basic creativity slider | Phase 4 | Not Started | Pending
Advisor | Safety | Number Checks | Highlight low-confidence numbers; underline with tooltip | Phase 3 | Not Started | Pending
Advisor | Safety | Citation Gate | Block answers without at least one citation | Phase 2 | Not Started | Pending
Advisor | Controls | Answer Length | Short/Medium/Verbose toggle | Phase 3 | Not Started | Pending
Advisor | Controls | Tone | Neutral/Executive/Analytical tone presets | Phase 4 | Not Started | Pending
Advisor | Prompts | Org Library | Org-wide saved prompts (admin curated) | Phase 4 | Not Started | Pending
Advisor | Prompts | Inline Variables | Prompt templates with {{variable}} inputs | Phase 3 | Not Started | Pending
Advisor | Memory | Session Memory | Persist last 10 Qs per user (local) | Phase 2 | Not Started | Pending
Advisor | Reports | One‑Pager | Generate one‑pager PDF with charts & citations | Phase 4 | Not Started | Pending
Advisor | APIs | Endpoint | POST /ai/ask with context payload (members) | Phase 5 | Not Started | Pending
Economy | Dashboards | Core Indicators | Predefined dashboards: GDP, inflation, unemployment | Phase 1 | Not Started | Pending
Economy | Visualization | Chart Builder | Dynamic charts: line, bar, pie, area | Phase 1 | Not Started | Pending
Economy | Viewing | Modes | Multiple views: summary, detailed, historical, forecasts | Phase 1 | Not Started | Pending
Economy | Filters | Dimensions | Filters by sector, geography, and time period | Phase 1 | Not Started | Pending
Economy | Data | Exports | Download/export charts, tables, raw data | Phase 1 | Not Started | Pending
Economy | AI | Insights | AI-generated insights: trends, anomalies, forecasts | Phase 2 | Not Started | Pending
Economy | Simulation | Scenarios | Scenario simulation tools for policy impact analysis | Phase 2 | Not Started | Pending
Economy | Alerts | Macroeconomic Events | Alerts for major economic changes or data releases | Phase 2 | Not Started | Pending
Economy | Collaboration | Annotations & Sharing | User annotations and sharing on charts | Phase 3 | Not Started | Pending
Trade | Dashboards | Trade Flows | Pre-built dashboards by product and country | Phase 1 | Not Started | Pending
Trade | Visualization | Comparatives | Comparative charts: imports vs exports, YoY | Phase 1 | Not Started | Pending
Trade | Maps | Partners | Interactive trade maps (partners, volumes) | Phase 1 | Not Started | Pending
Trade | Filters | Dimensions | Filters by trade type, commodity, time frame | Phase 1 | Not Started | Pending
Trade | Reports | Sectoral | Downloadable sectoral trade reports & analysis | Phase 1 | Not Started | Pending
Trade | Alerts | Shifts & Policy | Automated alerts for trade shifts/policy changes | Phase 2 | Not Started | Pending
Trade | Integrations | Customs | Integration with customs/trade databases | Phase 2 | Not Started | Pending
Trade | Watchers | Custom Watchlists | User-customizable watcher lists for trade metrics | Phase 2 | Not Started | Pending
Trade | Data | Exports | Export function for data and visualizations | Phase 1 | Not Started | Pending
Market Entry | Planning | Blueprint | Business plan builder with sector checklists | Phase 2 | Not Started | Pending
Market Entry | Scoring | Market Access | Automated market access scoring & risk indicators | Phase 2 | Not Started | Pending
Market Entry | CTAs | Contacts & Programs | Real-time CTAs: brokers, regulators, grants | Phase 2 | Not Started | Pending
Market Entry | Strategy | Scenarios | Scenario planning for growth & expansion | Phase 3 | Not Started | Pending
Market Entry | Research | Competition | Competitor density heatmaps & opportunity sizing | Phase 3 | Not Started | Pending
Market Entry | Reports | Environment | Customized business environment reports | Phase 3 | Not Started | Pending
Market Entry | Support | Mentoring | Feedback & mentoring request submission | Phase 2 | Not Started | Pending
Price Monitor | Dashboards | Live Prices | Live commodity/product price dashboards | Phase 3 | Not Started | Pending
Price Monitor | Tables | Comparisons | Price comparison tables by vendor/region | Phase 3 | Not Started | Pending
Price Monitor | Analysis | Volatility & Forecasts | Price volatility, trends, forecasting charts | Phase 3 | Not Started | Pending
Price Monitor | Alerts | Movements | User alerts for significant price moves/arbitrage | Phase 3 | Not Started | Pending
Price Monitor | Quality | Sources | Data source transparency & scraper health | Phase 3 | Not Started | Pending
Price Monitor | History | Trends | Historical price trend analysis | Phase 3 | Not Started | Pending
Price Monitor | Bulk | Uploads | Bulk product price upload & comparison | Phase 4 | Not Started | Pending
Price Monitor | Crowd | User Submissions | User-submitted price data with verification | Phase 4 | Not Started | Pending
Price Monitor | Integrations | Commerce | Integrations with e-commerce/retail platforms | Phase 4 | Not Started | Pending
Capital Access | Dashboards | Rates & Loans | Interest rate and loan product comparisons | Phase 2 | Not Started | Pending
Capital Access | Tools | Calculators | Financial calculators with up-to-date variables | Phase 2 | Not Started | Pending
Capital Access | Indicators | Banking Health | Banking sector health indicators & trends | Phase 3 | Not Started | Pending
Capital Access | Coverage | Fintech Data | Fintech products & emerging services coverage | Phase 3 | Not Started | Pending
Capital Access | Knowledge | Regulatory Updates | Reports, summaries, and regulatory updates | Phase 2 | Not Started | Pending
Capital Access | Alerts | Policy Changes | Alerts for banking policies/interest rate changes | Phase 2 | Not Started | Pending
Capital Access | Eligibility | Credit & Loans | Loan eligibility and credit scoring tools | Phase 4 | Not Started | Pending
Capital Access | Guidance | Personal Finance | User guidance for financial planning/investment | Phase 2 | Not Started | Pending
Capital Access | API | Data Access | API access for banking data integration | Phase 4 | Not Started | Pending
Regulatory Access | Guides | Sector Entry | Step-by-step market entry guides by sector | Phase 1 | Not Started | Pending
Regulatory Access | Database | Licensing Requirements | Searchable licensing requirement database | Phase 1 | Not Started | Pending
Regulatory Access | Workflows | Compliance | Interactive licensing workflows & checklists | Phase 2 | Not Started | Pending
Regulatory Access | News | Regulation | Real-time regulatory news & policy updates | Phase 2 | Not Started | Pending
Regulatory Access | CTAs | Government Portals | Direct CTAs to government portals/agencies | Phase 2 | Not Started | Pending
Regulatory Access | Risk | Timelines | Risk & timeline dashboards for licensing | Phase 2 | Not Started | Pending
Regulatory Access | Cases | Success Stories | Market entry case studies & success stories | Phase 3 | Not Started | Pending
Regulatory Access | Support | FAQs & Chatbot | Licensing FAQs and chatbot support | Phase 2 | Not Started | Pending
Regulatory Access | Tracking | Milestones | Visual milestone trackers for applications | Phase 2 | Not Started | Pending
Regulatory Access | Docs | Repository | Document/form repositories for applications | Phase 1 | Not Started | Pending
Regulatory Access | Alerts | Renewals | Alerts for due dates and renewals | Phase 2 | Not Started | Pending
Regulatory Access | Advisory | Legal/Regulatory | Access to legal/regulatory advisory services | Phase 3 | Not Started | Pending
Sector Intelligence | Reports | Benchmarks | Cross-sector benchmark reports & dashboards | Phase 2 | Not Started | Pending
Sector Intelligence | Charts | Sector Trends | Sector-specific performance & growth trends | Phase 2 | Not Started | Pending
Sector Intelligence | Widgets | Peer Benchmarking | Peer benchmarking with customizable metrics | Phase 3 | Not Started | Pending
Sector Intelligence | Integrations | Intelligence | Integrate industry news, reports, investment data | Phase 3 | Not Started | Pending
Sector Intelligence | Deep Dives | Subsectors | Subsector deep-dive & ecosystem mapping | Phase 3 | Not Started | Pending
Sector Intelligence | Funding | Investor Activity | Investor activity & funding trend dashboards | Phase 3 | Not Started | Pending
Sector Intelligence | Value Chain | Supply Chain | Supply/value chain visualization tools | Phase 4 | Not Started | Pending
Sector Intelligence | ESG | Indicators | ESG indicators by sector | Phase 4 | Not Started | Pending
Sector Intelligence | Briefs | Exports | Exportable industry intelligence briefs | Phase 2 | Not Started | Pending
Sector Intelligence | Heatmaps | Clusters | Interactive heatmaps: sector activity & clusters | Phase 4 | Not Started | Pending

## System_Screens
Area | Screen | Action | Route | Phase | Placement
UserApp | Saved Views | List, open, manage, share | /views | Phase 1 | Left rail (below modules)
UserApp | Dashboards | List, open, share | /dashboards | Phase 1 | Left rail (below modules)
UserApp | Datasets (read-only) | List datasets, schema, owner, freshness | /datasets | Phase 2 | Left rail (optional)
UserApp | Notifications | List alerts, subscribe/unsubscribe | /notifications | Phase 2 | Left rail (utility)
Help | Help Center | Docs, tutorials, data dictionary | /help | Phase 1 | Left rail (utility)
UserApp | Workspace Switcher | Switch workspace | /workspaces | Phase 1 | Left rail (bottom dock)
UserApp | Settings (Profile) | Profile, locale, theme, notifications | /settings/profile | Phase 1 | Top-right & bottom dock
Admin | Admin Hub | Org/Admin/Data consoles entry | /admin | Phase 1 | Left rail (bottom dock)
Org | Overview | Plan, usage meters, limits | /org/overview | Phase 1 | Admin Hub → Org
Org | Team & Roles | Invite, assign roles | /org/team | Phase 1 | Admin Hub → Org
Org | Billing | Plans, invoices, VAT | /org/billing | Phase 1 | Admin Hub → Org
Org | Branding & Settings | Logo/colors, locale, timezone | /org/settings | Phase 1 | Admin Hub → Org
Org | Security | MFA policy, SSO (Enterprise) | /org/security | Phase 2 | Admin Hub → Org
Org | Audit | Exports/shares audit | /org/audit | Phase 2 | Admin Hub → Org
Data | Sources | Connectors: Supabase, CSV; schedules | /data/sources | Phase 1 | Admin Hub → Data
Data | Uploads | XLSX/CSV upload, schema detect, PII tags | /data/uploads | Phase 1 | Admin Hub → Data
Data | Catalog | Datasets, owner, freshness SLA | /data/catalog | Phase 1 | Admin Hub → Data
Data | Policies | Row/Field-level security (Ent) | /data/policies | Phase 3 | Admin Hub → Data
Data | Quality | Schema/freshness/null tests + alerts | /data/quality | Phase 3 | Admin Hub → Data
Data | Lineage | Upstream/downstream graph (MVP) | /data/lineage | Phase 3 | Admin Hub → Data
Admin | Integrations | Slack/webhooks, email provider, PSP keys | /admin/integrations | Phase 1 | Admin Hub
Admin | API Keys | Create/revoke keys; scopes | /admin/api-keys | Phase 2 | Admin Hub
Admin | Status | System status/incidents link | /admin/status | Phase 1 | Admin Hub
Auth | Signup | Email+Password, Magic Link | /auth/signup | Phase 1 | Standalone
Auth | Login | Password, Magic, SSO | /auth/login | Phase 1 | Standalone
Auth | Forgot Password | Reset flow | /auth/forgot | Phase 1 | Standalone
Auth | MFA | TOTP + backup codes | /auth/mfa | Phase 2 | Standalone

## Roles
Role | Can View | Can Create | Can Manage | Export Limit | Notes
End User | 8 modules + Saved Views/Dashboards | Saved Views/Dashboards | — | Plan-based | RLS enforced
Org Admin | User app + Org console | Invites, workspaces | Team, roles, billing, org settings | Unlimited | No data-source ops unless also Data Admin
Data Admin | User app + Data console | Sources, uploads, datasets | Catalog, Quality, Policies (RLS/FLS), Lineage | Unlimited | No billing
Platform Admin | Tenant metadata | Support actions | Tenant ops (audited, time-bound) | — | No customer data by default

## Entitlements_Matrix
Plan | Role | Module | Feature | Limit/Value | Flag
Free | End User | all | Saved Views | max=3 | views.max=3
Free | End User | all | Dashboards | max=1 | dash.max=1
Free | End User | Price Monitor | Export rows | max=1000 | export.rows.max=1000
Free | End User | all | Scheduled Reports | disabled | scheduler.enabled=false
Free | End User | all | API | disabled | api.enabled=false
Free | Org Admin | Org | Seats | max=1 | seats.max=1
Free | Data Admin | Data | Connectors | max=0 | connectors.max=0
Pro | End User | all | Saved Views | unlimited | views.max=-1
Pro | End User | all | Dashboards | unlimited | dash.max=-1
Pro | End User | all | Export rows | max=100000 | export.rows.max=100000
Pro | End User | all | Scheduled Reports | enabled | scheduler.enabled=true
Pro | End User | all | Slack/Webhooks | enabled | integrations.slack_webhook=true
Pro | End User | all | API | read | api.read=true
Pro | Org Admin | Org | Seats | max=5 | seats.max=5
Pro | Data Admin | Data | Connectors | max=1 | connectors.max=1
Enterprise | End User | all | Whitelabel | enabled | brand.whitelabel=true
Enterprise | Org Admin | Org | SSO | enabled | sso.enabled=true
Enterprise | Org Admin | Org | Custom roles | enabled | roles.custom=true
Enterprise | Org Admin | Org | Audit export | enabled | audit.export=true
Enterprise | Data Admin | Data | RLS/FLS | enabled | rls.fls=true
Enterprise | Data Admin | Data | Connectors | min=3 | connectors.max=3
Enterprise | Data Admin | Data | API | read/write | api.write=true

## IA_README
Key | Value
Left Sidebar | Top = 8 modules only. Below = Saved Views, Dashboards, Datasets (optional), Notifications, Help. Bottom dock = Workspace Switcher, Settings, Admin.
Top Bar | Breadcrumb, global search, quick create, share, user menu.
Auth | Standalone: /auth/signup, /auth/login, /auth/forgot, /auth/mfa.
Consoles | Org/Data/Admin live under Admin Hub; not main tabs.